Meeting Minutes of the

Northwestern Chester County Municipal Authority

May 28, 2025

The meeting was called to order by Chairman David Eames at 7:00 PM.

Present for roll call were: Mr. Bill Ford, Mr. Matt Halvorsen, Mr. Michael Kern, Mr. Bill Kennedy, Mr. Eric Olsen & Mr. David Eames.

Also present were:  Mr. Derek Ink, Operator in Charge, Mr. Alex Bar, Engineer, Ms. Stephanie Kern, Administrator and Ms. Kristin Camp, Solicitor.

The minutes of the April 23rd, 2025 meeting were approved on a motion by Matt Halvorsen and seconded by Eric Olsen.  Motion carried.

The Treasurer's Report for march was accepted on motion by Eric Olsen and seconded by Mike Kern. Motion carried.

PUBLIC COMMENTS:    None

CORRESPONDENCE: 1) There was a note from Eileen Dillow thanking NCCMA for the donation to the Honey Brook Presbyterian Church in the memory of James Dillow.   2) NCCMA got the approval for the tax exemption for the school taxes for 3641 Horseshoe Pike from the Chester County Board of Appeals.  There was a discussion about getting a refund for the prorated taxes paid at settlement.  It was decided to send a letter to the Twin Valley School District asking for reimbursement for the 2025 taxes that were paid at settlement. 3)  There was a phone call from a customer complaining about the noise from West Pump Station in the middle of the night.

ADMINISTRATOR'S REPORT: Stephanie Kern

SOLICITOR’S REPORT:   Kristin Camp

OPERATOR'S REPORT: Derek Ink

- Daily monthly flow for April averaged 387,000 gallons per day. The discharge monitoring report (EDMR) was submitted to DEP. There were 3 exceptions to the permit, Ammonia Nitrogen average monthly lbs./day 53.0, (limit 40.5 lbs./day), and Ammonia Nitrogen average monthly concentration 26.8 mg/l (limit 8.1 mg/l), total nitrogen average monthly concentration 32.4 mg/l (limit 28.8 mg/l).

- Inspections:

-221, 223 Chastain Drive (Chestnut Ridge)

-524 Sativa Drive (Chestnut Ridge)

-418, 401 Crenata Drive (Chestnut Ridge)

-110, 112 Sycamore Drive (Honey Ridge)

-550 Pequea Ave (Honey Brook Hardware)

- Received and responded to 71 Pa one calls.

- Plant Upgrade:

- Pac 2 installed drainage basin, final grading in some areas, working on installing blower piping in building and connecting it to air lines to primary lagoons, and mbbr tank

- BSI installed conduit from blower building to mbbr tank, installed lighting, vfd’s, and control panels in mbbr building and blower building

- Moxie mechanical working on completing hvac system in blower building

- Pipe Data cleaned and televised 31,654 ft of pipe between May 5 and May 14. There were no significant deficiencies in the televised main such as infiltration, cracked pipe, or spalling pipe.

- Village Green:

-pump 1 valve was replaced by MGK industries, staff conducted a draw down test to see if this helped the pump gpm

-GIS still needed

- Office Property:

-Pricing to pave the rest of the driveway Lyons & Hole $12,450, B.F.Brown $14,750, Beiler Paving $17,500.  A motion was made by Matt Halvorsen and seconded by Eric Olsen to accept the quote from Lyons & Hole.  Motion Carried.

- Staff made repairs to lagoon pump 2 electrical equipment after it was damaged due power failure at the plant.

- Staff shocked and cleaned the sand filters and chlorine contact tank due to algae. We are still trying to utilize the sand filters as much as we can until they get rehabilitated in the fall.

ENGINEER'S REPORT: Alex Bar

OLD BUSINESS:

1.  Chestnut Ridge – No Update

.         2.  Act 537 – The Act 537 has been approved by DEP.

3.  Village Greene- HRG Report

4.  Honey Brook Estates-No Update

5.  Syncarpha- No Update.

6.  Mobile Reality 3/UMH/Struble Ridge – No Update

7.  Old Maple Inn Estates – No update.

8.  WWTP upgrade/PennVest loan-HRG Report

9.  Keystone Court- A motion was made by Matt Halvorsen and seconded

by Mike Kern to approve the escrow release of $191,838.00 contingent

upon the payment of the construction review escrow.  Motion carried.

10.  Zook Molasses/Upward Investments – No update

11.  West Pump Station/upgrade- HRG is working on the final design.

12.  Twin County Business Park- No Update.

13.  Arbor’s Glen-HRG Report- The Authority had previously submitted a

Will Serve letter to Arbor’s Glen allowing them to have 170 EDUs.  The

Developer is now seeking 200 EDUs of sewer capacity.  There was a

discussion about the capacity left at the Cupola basin and future

development.  It was decided that the Authority needed to have a meeting

with the Township regarding this issue.

14.  Honey Brook Hardware- HRG Report.

15.  Tri County Investment Group-No update.

16.  Calvary Church – No Update

17.  Chester County Solid Waste Authority- No update.

18.  Vernon MacIntyre (3766 Horseshoe Pike) – The udated plan will require

3 EDUs.

NEW BUSINESS:

- A motion was made by Bill Ford and seconded by Mike Kern to approve the Pact Two, LLC payment #8 in the amount of $271,214.95 for submission to PennVest.  Motion carried.

- A motion was made by Mike Kern and seconded by Eric Olsen to approve the Moxie Mechanical payment #7 in the amount of $20,700.00 for submission to PennVest.  Motion carried.

- A motion was made by Matt Halvosen and seconded by Eric Olsen to approve payment #3 for BSI Electric in the amount of $355,500.00 for submission to PennVest.  Motion carried.

- A motion was made by Eric Olsen and seconded by Matt Halvorsen to approve payment #8 for HRG in the amount of $69,875.36 for submission to PennVest.  Motion carried.

- A motion was made by Bill Ford and seconded by Eric Olsen to approve the Herbein & Company, Inc. quote for the 2023/2024 audit.  Motion carried.

- A motion as made by Bill Ford and seconded by Eric Olsen to

approve the Moxie Mechanical change order #1 increase of $6,058.70 for submission to PennVest.  Motion carried.

There being no further business to come before the board, a motion was made by   Bill Ford and seconded by Bill Kennedy to adjourn the meeting at 8:30 PM. Motion carried.

Respectfully submitted,

Michael Kern
       Secretary